## Table of contents
DTU’s best practice for
Research Project Administration
Externally funded research projects – UK95/97
Co-financed research projects
Purpose
This guideline aims to provide a helpful overview over what to do and where to get help during all the steps of an externally funded research project.
The aim of this guideline is also to make sure, that it is easy to see which tasks are mandatory to perform, in order to ensure compliance with rules and legislation.
Target groups
The target groups are Project Managers and the department administrations that provides administrative support to Project Managers on externally financed projects, e.g. Project Coordinators, secretaries, Research Coordinators, fundraisers etc.
Note that as an applicant and as a grant holder, the responsibility for all tasks ultimately lies with the Project Manager.
Projects not covered by “DTU’s best practice for Research Project Administration” procedures
This document does not cover the procedures for commissioned research or projects with no external funding. However, regardless of source of financing, you must always observe legal regulations regarding ethics, GDPR, export control, Nagoya and ABC. And always observe DTU procedures regarding data management plans, publishing, entering contractual and binding agreement, procurement, filing, hiring staff etc.
Please consult the Project Office or the Project Controller if in doubt whether a project is defined as commissioned research, before sending it to DTU Legal & Contracts (Legal) for review.
You can read about the differences between co-financed research and commissioned research on DTU Inside (note: the information is currently only awailable in Danish): | Projekttype
Contents
1. Pre-Grant
In the pre-grant phase, you elaborate and work on the application to be submitted to a Funding Body. Writing a competitive and qualified application is a significant and big task with many sub-tasks.
The tasks included in the Pre-Grant phase are:
1.1. Refine the idea
1.2. Prepare the writing process
1.3. Write the application
1.4. Finalize and submit. File the application and budget in DTUDOCX
2. Grant
Some funding providers require a contract between themselves and the coordinator of a project. This is the case for EU-financed projects, where a Grant Agreement (GA) needs to be entered between the coordinator of a consortium and the EU before the project can start.
Regarding grants from the Innovation Fund Denmark (IFD), you will be invited to contract negotiations, where an investment agreement between all partners and the IFD will be negotiated and agreed upon prior to project commencement.
A consortium agreement also needs to be negotiated and agreed upon between the project partners: A consortium agreement is a contract about project organization, Intellectual Property Rights (IPR), etc.
The consortium agreement should always be agreed on before the project starts. However, sometimes negotiations are not completed until after project setup and start. A consortium agreement can also be called a cooperation agreement or a collaboration agreement.
Tasks included in the Negotiation phase are:
2.1. Grant / Grant Agreement Considerations
2.2. Negotiate the Collaboration Agreement
2.3. Sign the Collaboration Agreement and file it in DTUDOCX
2.4. If your project involves processing of personal data: negotiate and sign agreeements on joint data controllership, data processing or disclosure
2.5. Decide on data publication, data sharing and long term preservation
3. Post-Grant
When a project has been granted by a Funding Body and accepted by the Department, and the legal contracts are in place, the ongoing research and administration take place until the project is closed.
The financial processes of project administration are described in detail in AØR's material regarding Project Administration on DTU Inside (currently only awailable in Danish): | Projektøkonomi
The tasks included in the Post-Grant phase are:
3.1. Prepare administrative tasks for project setup
3.2. Do ongoing project administration and budget follow-up
3.3. Collaborate with partners
3.4. Make ongoing reporting
3.5. If you make changes to the project
3.6. Disseminate project results
3.7. Close the project
Pre-Grant
Pre-Grant
Post-Grant
Grant

## PRE-Grant
Task | Sub-task | Mandatory? | Action | Considerations / Advice | Tool / Information | Who can help? | Who is responsible? | Who signs / approves?
1.1. Refine the idea
| Sub-task | Mandatory? | Action | Considerations / Advice | Tool / Information | Who can help? | Who is responsible? | Who signs / approves?
| Search for a call that matches the idea |  | Define and describe the problem to be solved. | Why is the problem important? |  | Project Office, Colleagues | Project Manager
If successfully solved, what will be the impact?
Who will benefit from the solution?
Is the timing right?
|  |  |  | Consult the Research Office, Research Support DTU's lists of funding opportunities. | Funding for your research - DTU Inside | Research Support (101)
| Assess potential security risks (theft, espionage) |  |  | Consider potential challenges and risks (such as theft or espionage) related to the project idea and the intended project set-up. | DTU Guidance on international partnerships | Project Office, Colleagues | Project Manager
PET - is your research at risk?
| Give thought to general rules and regulations |  |  | Consider the following: |  |  | Project Manager
|  |  |  | DTU's principles for good scentific conduct. | Principles for good scientific conduct - DTU Inside | Research Support (101)
Does the scientfic idea involve:
|  |  |  | Technology that is regulated by export control (dual use potential)? | Dual-use - DTU Inside | Research Support (101)
|  |  |  | Requirements for ethical approval or other regulatory authorisations (e.g. involving human participants, human tissue/data, medical devices, animal research, or other legal requirements)? Are theres ethical concerns that should be addressed, even where no formal approval is required? | Research ethics (ethical approvals, permits and other ethical concerns) | Research Support (101)
|  |  |  | Using biological materials in your research? Ensure to comply with regulations on non-human genetic ressources (Nagoya protocol/Access and Benefit Sharing (ABS) regulations)) | Nagoya protocol (Access and Benefit Sharing regulations) | Research Support (101)
Research Support (101)
|  |  |  | Personal data | GDPR at DTU | GDPR Support
| Get approval of the scientific idea | Mandatory | Get approval of the scientific idea. | The scientific idea must be approved to ensure, that the project idea is in line with the Department's research strategy and that the project can be accommodated. |  | Project Office | Project Manager | Department Management
Follow the Department’s procedure for internal approval of the research idea.
Respect internal deadlines.
| Search for an instrument that matches the project idea |  |  |  | Funding for your research - DTU Inside | Research Support (101), Project Office, Colleages | Project Manager
| Prepare a draft for the project economy |  |  | Consider the costs of |  | Project Office | Project Manager
- staffing
- equipment, infrastructure
- travelling, conferences
Consider potential challenges and risks (such as theft or espionage) related to the project idea and the intended project set-up.
|  |  |  | Consider budget for data management and FAIR data (incl. Skills) | Design & plan for research data management | DTU Library
|  |  |  | Consider budget for open access publishing | Funder requirements and costs of research data management | DTU Library
|  |  |  | etc. | How to publish Open Access | DTU Library
| Get internal approval of project economy | Mandatory | Make sure Department Management approves of the preliminary project economy. | Is the project aligned with the overall Department strategy and economy? |  | Project Office | Project Manager | Department Management
| Build a complete and strong consortium |  | Define the competences needed and target the search for partners. |  |  |  | Project Manager
|  |  | Consider which partners to involve in the project. If necessary, conduct a risk evaluation. |  |  | Research Support, Colleagues
|  |  | Form the consortium. |  |  | Network
|  |  | Check the eligibility of the consortium partners. |  |  | Project Office
Request a conditional yes for participating from all partners.
Act on possible conflicts of interest between partners.
|  |  |  | Consider whether a Non Disclosure Agreement (NDA) with partners is needed. | For forskere - DTU Inside, Legal | Contract Responsible
1.2. Prepare the writing process
| Sub-task | Mandatory? | Action | Considerations / Advice | Tool / Information | Who can help? | Who is responsible? | Who signs / approves?
| Register on the application portal |  | If relevant: |  |  | Project Office | Project Manager
|  |  | Find and select the relevant call on the electronic platform. |  | Funding for your research - DTU Inside
|  |  | Fill out the administrative forms as early as possible. |  |  | Research Support (101)
If coordinator:
|  |  | Collect administrative data from the partners and fill out the forms. |  |  | Research Support (101)
| Plan for the Data Management Plan |  | Check funder requirements for delivering af Data Management Plan (DMP). |  | Planning research data management - DTU Library | DTU Library | Project Manager
[5 empty] | Data Management Plan | DTU Library
| Plan for Open Access |  | Consider funder- and DTU requirements for Open Access (OA) publishing of research papers. |  | Publishing Open Access |  | Project Manager
DTU Publication Policy
| Plan for FAIR data (“Findable”, “Accessible”, “Interoperable” and “Re-usable”) |  | Check funder requirements for FAIR and Open Data. FAIR is an acronym for “Findable”, “Accessible”, “Interoperable” and “Re-usable” |  | Funder requirements and costs of research data management - DTU Library | DTU Library | Project Manager
The FAIR Principles
Publishing research data - DTU Library
| Communicate the project framework to the partners |  | If coordinator: |  |  |  | Project Manager
|  |  | Ensure that all partners involved know the call’s terms and conditions. |  |  | Research Support (101)
|  |  | Settle the total budget and the budget per partner. Withhold a budget share for unexpected needs. |  |  | Project Office
Agree on who writes what and the time frame for the writing process.
Ensure that everybody is committed to the writing process.
|  | Filing mandatory | Create a case for filing in DTUDOCX if none such exists. File all written communication with external participants in DTUDOCX. |  | DTUDOCX | DTUDOCX Support
| Decide on the need for use of infrastructure and internal resources |  |  | Consider informing and involving all relevant parties, if the project requires significant experimental facilities, IT infrastructure or TAP resources from within the Department, and include it in the budget. |  | Project Office | Project Manager
| Get DTU support |  | Inform relevant persons/functions about the need for support and agree on a timeline for and extent of support. | Consider the need for support e.g. for: | Research, innovation and consultancy - DTU Inside | Project Office | Project Manager
|  |  |  | the writing itself, text input, review, comments, proof reading | Funding your research | Research Support (101)
illustrations: consider the use of a graphic designer
|  |  |  | the budget |  | Project Controller
|  |  |  | legally binding documents e.g. Non Disclosure Agreement, NDA, Letter of Support, LoS, Memorandum of Understanding, MoU, etc. |  | Legal
IPR related issues (consider if the IP brought into the project and the IP created in the project is something DTU and could be interested to sell in the future) - scout for third party rights at departmental level
|  |  |  | Business plan/Business Model Canvas |  | Project Office
|  |  |  | GDPR issues | Who does what at DTU? - DTU Inside | GDPR Office
| Consider hiring proces/staffing |  | Consider time for staffing. | If you expect to hire staff through advertisement, consider time needed for hiring new staff, including job advertisement, interviews and negotiations (and, if relevant, check of background). Most candidates also need time to resign from their current position. Evaluation might require additional time. |  | AHR, Recruitment and Onboarding | Project Manager
As a rule, expect at least:
|  |  |  | DK staff: 3-4 months plus resignation | Recruitment and onboarding
EU staff: 4 months plus resignation
Non-EU: 6 months plus resignation
High-risk countries: more than 6 months
| Get external support |  | Create a case for filing in DTUDOCX if none such exists. File all written communication with external participants in DTUDOCX. | For large collaborative applications with DTU as a coordinator, you may consider working with Innovayt on specific sections of the application. Innovayt is DTU’s chosen external partner and the only procurement partner that you are allowed to work with for funding assistance. Contact Procurement for information | Frontpage - Innovayt | AØR Procurement | Project Manager?
Procurement
|  | Filing mandatory |  |  | DTUDOCX | DTUDOCX Support
1.3. Write the application
| Sub-task | Mandatory? | Action | Considerations / Advice | Tool / Information | Who can help? | Who is responsible? | Who signs / approves?
| Describe the project |  | Choose a title and acronym. |  |  | Project Office | Project Manager
|  |  | Write an abstract. | No abbreviations in the abstract. |  | Research Support (101)
|  |  | Shortly present the project, solution, expected results and impact to capture the evaluators’ interest. | Take into account, that evaluators are not necessarily experts in the specific field. |  | Co-writers
|  |  | Use key words from the call text. |  |  | Partners
|  |  | Make a project description. | If you intend to hire anyone on the call you could consider getting in touch with AHR now already to ensure you are able to hire the person/people you have in mind, where applicable | Recruitment and onboarding | AHR, Recruitment & Onboarding
Write and align the project description with the call text.
Specify the particular persons that will be working on the project.
| Prepare the internal budget | Mandatory | Use the DTU Budget Template to make the internal budget. Always get an updated version from Project Controller. | Upon request your Project Controller will send you the latest DTU budget application template updated with the most recent hourly rates. You can fill in the budget yourself or your PC can assist you. PC will review final budget and ensure compliance with the funding body’s rules and guidelines. | NOTE: This information is currently only available in Danish.
[5 empty] | Projektansøgning | Project Controller | Project Manager
[5 empty] | Projekttype | Project Controller
|  |  | Project Controller should control that the budget is aligned with Funding Body’s guideline. | Consider staff and allocation of hours. See DTU guideline for time and salary allocation on DTU Inside. | Planning and managing time - DTU Inside | Project Controller
|  |  | Obtain all relevant approvals of the budget from the Department Management. | Consider operational expenses e.g. procurement and travel. | Styre projektøkonomi | Project Controller |  | Department Management
Consider DTU standards on overhead (OH), fixed assets, and salary.
Consider infrastructure and internal resources (TAP, laboratory, supercomputing, administrative support, maintenance, etc.).
Consider PhD students and their financing in the project (incl. co-financing).
Consider co-financing and check its compatibility with the Department’s rules on this matter.
Note: Leave time for Project Controllers final check of the budget for eligibility criteria and compliance with Department rules.
| Prepare budget in Funding Body’s template |  | Transfer the internal budget to Funding Body’s budget template. | Project Controller can help clarify if funding body’s template differs from DTU budget template. |  | Project Office | Project Manager
|  |  | If coordinator: |  |  | Project Controller
Collect budgets from all partners. Request that the collected budgets are on the call’s budget scheme.
Consolidate the project’s total budget on the call’ budget schemes.
| Get CV and publication list for key persons |  | Prepare the CV and collect CVs from other key persons in the project organization in the format requested by the Funding Body. | Target the content of all CVs to the call. |  | Project Office | Project Manager
| Check for other requirements from funding body |  | Draft mandatory sections based on the specific project, e.g. Ethics, Impact, Value creation, Gender, Dissemination, Risk and Contingency Plan, Data Management, GDPR. |  |  | Project Office, Research Support (101) | Project Manager
| Decide on terms and conditions for the collaboration agreement |  | Ensure that the collaboration agreement with external partners addressing access rights during a project, IP, etc. are in place. |  |  | Project Office | Project Manager
|  |  | Ensure that the collaboration agreement on the research project is both legal and in compliance with DTU’s policies (a.o. IPR, confidentiality, rights options and licenses), and is checked by the legal department before signing and project start. |  | Legal and Tech Transfer | Legal
|  |  | Ensure that the collaboration agreement on the research procect is in compliance with GDPR rules and regulations. |  | GDPR at DTU - Protection of personal data - DTU Inside | GDPR Office
| Give thought to general rules and regulations | Mandatory |  | Consider the following: | Good scientific conduct | Research Support (101) | Project Manager
|  |  |  | Is the technology in the project regulated by export control (dual use potential)? | Dual-use - DTU Inside | Research Support (101)
|  |  |  | Requirements for ethical approval or other regulatory authorisations (e.g. involving human participants, human tissue/data, medical devices, animal research, or other legal requirements)? Are there ethical concerns, that should be addressed even where no formal approval is required? | Research ethics (ethical approvals, permits and other ethical concerns) | Research Support (101)
|  |  |  | Using biological materials in your research? Ensure to comply with regulations on non-human genetic ressources (Nagoya protocol/Access and Benefit Sharing (ABS) regulations)) | Nagoya protocol (Access and Benefit Sharing regulations) | Research Support (101)
| Get enclosures |  |  |  |  | Project Office DTUDOCX Support | Project Manager | Head of Department
If relevant: Get letter of commitment from partners.
If relevant: Get signature for DTU Letter of Support (LoS).
|  | Filing mandatory | Create a case for filing in DTUDOCX if none such exists. File the signed agreement in DOCX. |  | DTUDOCX
1.4. Finalize and submit
| Sub-task | Mandatory? | Action | Considerations / Advice | Tool / Information | Who can help? | Who is responsible? | Who signs / approves?
| Get the Department Managements approval of the research grant application | Mandatory | Ensure that the research application is submitted in accordance with DTU's principles for responsible use of generative Artificial Intelligence (AI). |  | Attention points and tools to check research grant applications - DTU Inside | Research Support (101) | Project Manager | Head of Department
Research Application Declaration
| Submit the application |  |  | Make sure that all the documents are in the requested format. |  | Project Office | Project Manager
Upload the application in due time. Often the submission portal is busy.
If coordinator:
Submit signed applications to the Funding Body.
Distribute the uploaded application (time-stamped version, if available) to the partners as well as the receipts confirming successful upload of the application.
If partner:
Retrieve the application with all related documents from the coordinator.
| File application in DOCX | Update case in DTUDOCX or create one if none such exists. Filing mandatory | By this stage it is mandatory to create a case for filing in DTUDOCX if none such exists. File the application including all appendices in DTUDOCX. File all further communications with the Funding Body relating to the application in DTUDOCX. | An instruction to DTUDOCX Research Cases is available on DTU Inside. | DTUDOCX | Project Office | Project Manager
Send copies of applications to partners.
|  | Filing mandatory | File these copies in DTUDOCX. |  | DTUDOCX | DOCX Support
| Act on the response from the Funding Body |  |  | If relevant, consider refining the proposal and resubmit. |  | Research Support (101) | Project Manager
|  |  | If coordinator / if no partner and invited for interview: |  |  | Project Office
Contact the Research Office, Research Support DTU, for interview training for chosen applicants - if relevant.
If granted:
|  | Filing and updating mandatory | Register the Grant Letter or invitation to enter a Grant Agreement (GA) / Investment agreement in DTUDOCX. Update case in DTUDOCX |  |  | DOCX Support
|  |  | Fill out information in DTUDOCX about granted amount, Overhead-rate, project period, etc. |  | DTUDOCX | Project Office, DTUDOCX Support
If rejected:
|  |  | File the rejection letter in DOCX and fill in information about the date of rejection. |  | DTUDOCX
|  | Filing mandatory | Close the DTUDOCX case. Sker automatisk to dage efter Grant status er blevet opdateret på sagen. |  |  | DTUDOCX Support
Note on G82: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Irene: Det er faktisk DTU Indkøb som står for det og har informationerne - pt. kan jeg ikke finde noget på det nye Inside.
Note on F83: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Irene: Det er faktisk DTU Indkøb som står for det og har informationerne - pt. kan jeg ikke finde noget på det nye Inside.

## Grant
Task | Sub-task | Mandatory? | Action | Consideration/Advice | Tool / Information | Who can help? | Who is responsible? | Who signs / approves?
2.1. Grant / Grant Agreement Considerations
| Sub-task | Mandatory? | Action | Consideration/Advice | Tool / Information | Who can help? | Who is responsible? | Who signs / approves?
| Confirm acceptance of the Grant |  | If coordinator/if no partners: |  |  | Project Office | Project Manager
|  | Filing mandatory | File the acceptance in DTUDOCX on the research case, stating a clear name (document folder type must be “Document” and document folder topic must be “Granted / Rejected / Other reason”). | The Research Office, Research Support DTU, has a guide available that covers the process of the Grant Agreement Preparation (GAP) between the Consortium of a successful Horizon Europe (HE) proposal and the European Commission (EC). The guide is for collaborative projects. Contact Faton Avdijaj for a copy: favdij@dtu.dk | DTUDOCX | DOCX Support
Update research case in DTUDOCX.
If partner:
|  |  | File the acceptance in DTUDOCX on the research case with a clear name (document folder type must be “Document” and document folder topic must be “Granted / Rejected / Other reason”). |  | DTUDOCX | DOCX Support
|  | Filing mandatory | Update research case in DTUDOCX. |  | DTUDOCX
| Inform the partners |  | If coordinator: | If the grant is in cooperation with another university please consider getting in contact with AHR in order to discuss the best recruitment proces for DTU | Recruitment and onboarding | AHR Recruiment & Onboarding
|  |  | Inform the partners about the good news and the forthcoming process and relevant deadlines. |  |  | Project Office
|  |  | Clarify contact details with partners regarding the person(s) who will negotiate contracts on behalf of the partner. |  |  | Legal
2.2. Negotiate the Collaboration Agreement
| Sub-task | Mandatory? | Action | Consideration/Advice | Tool / Information | Who can help? | Who is responsible? | Who signs / approves?
| Negotiate collaboration agreement | Mandatory | When you have received the grant, contact your contract responsible. The contract responsible will contact Legal. |  | For researchers - DTU Inside | Contract Responsible, Legal | Legal, Project Manager
2.3. Sign the Collaboration Agreement and file it in DTUDOCX
| Sub-task | Mandatory? | Action | Consideration/Advice | Tool / Information | Who can help? | Who is responsible? | Who signs / approves?
| Obtain all required signatures |  | If coordinator: |  |  | Project Office | Project Manager | Department Management / Head of Department / President
|  | Mandatory | Obtain signatures from:
|  |  | Partners |  |  | Contract Responsible
|  |  | The authorized Legal signatory on behalf of DTU |  | Accounting Instructions - DTU Inside | NOTE: This information is currently only available in Danish.
Funding Body
If partner:
|  | Mandatory | Obtain signatures from:
The authorized signatory on behalf of:
|  |  | the Department |  | Accounting Instructions - DTU Inside | NOTE: This information is currently only available in Danish.
the Funding Body
| Forward final Collaboration Agreement to partners |  | If coordinator: |  |  |  | Project Manager
|  |  | Ensure that the final Collaboration Agreement has all signatures and appendices before sending it to the partners. |  |  | Project Office
| File Collaboration Agreement in DOCX | Filing mandatory | File the full and final Collaboration Agreement with all signatures and attached appendices in DTUDOCX on the research case stating a clear file name. |  | DTUDOCX | Project Office, DTUDOCX Support | Project Manager
- Document folder type: “Document”
- Document folder topic: “Granted / Rejected / Other reason”.
- Choose “Signed research agreement” and select type of research agreement.
Update research case in DTUDOCX.
2.4. If your project involves processing of personal data: negotiate and sign agreeements on joint data controllership, data processing or disclosure
| Sub-task | Mandatory? | Action | Consideration/Advice | Tool / Information | Who can help? | Who is responsible? | Who signs / approves?
| Negotiate relevant GDPR agreement | Mandatory | Agree on conditions and roles for processing of personal data in the project with your project partners. | Applicable if you need to receive/share personal data with partners or students during your project or you use external services to process data. | GDPR at DTU | Personal Data Coordinator GDPR Office | Project Manager
| Sign relevant GDPR agreement | Mandatory | Sign relevant agreement/s with project partners. File the agreements in the project GDPR case in DTUDOCX. | Applicable if you need to receive/share personal data with partners or students during your project or you use external services to process data. | DTUDOCX | Personal Data Coordinator GDPR Office | Project Manager | Legal Signatory assigned by DTU/Department
2.5. Decide on data publication, data sharing and long term preservation
| Sub-task | Mandatory? | Action | Consideration/Advice | Tool / Information | Who can help? | Who is responsible? | Who signs / approves?
| Decide on data publication and sharing and long term preservation |  | Consider regulations and legal aspects, that can have implications for data publication and sharing (i.e. IPR, GDPR, Patents, sensitive data). | Update the DMP with any agreements that affect data and software publication. | Data management plans | Project Office, DTU Library, Legal, Personal Data Coordinator, GDPR Team | Project Manager
Publish & Share your research data
|  | Mandatory | File revised documents in DTUDOCX |  | DTUDOCX | DTUDOCX Support

## POST-Grant
Task | Sub-task | Mandatory | Action | Considerations/Advice | Tool / Information | Who can help? | Who is responsible? | Who signs / approves?
3.1. Prepare administrative tasks for project setup
| Sub-task | Mandatory | Action | Considerations/Advice | Tool / Information | Who can help? | Who is responsible? | Who signs / approves?
| Initiate the financial project setup | Mandatory | Create a financial project in the financial systems: Send the Grant Application, Grant Letter, Grant Agreement or Investment Agreement including all the appendices, to the Project Controller via workflow in DOCX. |  | Projektoprettelse | Project Office, Project Controller, DTUDOCX Support | Project Manager | Department Management Head of Department
|  |  | Ensure that the latest internal budget version incl. an initial plan for staff allocation during the project period is included. | Note: If the project needs to start and there is not yet a signed grant letter, grant agreement or investment agreement, then ask for a declaration signed by Head of Department: “Direktør Erklæring” – the template for this statement can be obtained from Project Controller. |  | Project Controller
|  |  | The Project Controller then creates the project in the financial systems at DTU and communicates the project number to the Project Manager. |  | DTU Fusion | Project Controller
|  | Filing mandatory | File the documentation for the Department Managements approval (1. or 2.) in DOCX. |  | DTUDOCX | Project Office, DOCX Support
| Initiate a start-up meeting, if relevant |  |  | A start-up meeting between Project Manager, Project Office and Project Controller can be arranged, if it is useful. |  | Project Office | Project Manager
|  |  |  | A start-up meeting can serve to establish a common understanding of the project set-up and ensure clarity regarding the project structure, financial conditions, scheduling of reporting periods, and overall account structure to provides an adequate financial overview during the project lifetime. |  | Project Office
| Prepare Data Management Plan |  | A Data Management Plan (DMP) is required for all research projects at DTU (Ph.D. and up) | Read DTU’s Research Data Management Policy as well as Department / Centre-specific guidelines. | DTU Research Data Management Policy | Project Office | Project Manager
|  | Mandatory | Make the Data Management Plan on DeIC DMP or use local template. | The DMP outlines how to make data FAIR. DTU expects research data to be FAIR (“Findable”, “Accessible”, “Interoperable” and “Re-usable”). | https://dmp.deic.dk/ | DTU Library
|  |  | Update the Data Managment Plan on a regular basis. File the updated version in DTUDOCX | Note: Check for special requirements from funding agencies. | DMP - DTU Library
|  |  | Share the Data Management Plan with the local Data Responsible if required by Department. |  |  | Local Data Responsible
File the Data Management Plan according to Department procedure.
|  |  |  | Note: On EU projects, the DMP is a deliverable and it is important to use the Horizon Europe template, which is available when you have logged on to DeIC DMP. |  | DTU Library
| Personal data: Consider GDPR issues. |  | Comply with GDPR-requirements and prepare relevant GDPR documentation (see list below). | Read about the General Data Protection Regulation (GDPR) and find relevant templates for processing records and agreements on DTU Inside. Align GDPR with the Data Management Plan if possible, but GDPR-documentation is mandatory in its own right | GDPR at DTU - Protection of personal data - DTU Inside | Personal Data Coordinator | Project Manager | Legal Signatory assigned by DTU/Department
|  | Mandatory | Prepare a data processing record for the project, and establish legal basis for processing, set deletion dates etc. |  | GDPR at DTU - Protection of personal data - DTU Inside | Personal Data Coordinator
|  | Mandatory | Inform the data subjects if you are collecting personal data for a research project. | Note: Your local Personal Data Coordinator is the first point of contact for GDPR related matters. |  | Personal Data Coordinator GDPR Office
|  | Mandatory | Finish applicable GDPR-contracts (for example on data processing or joint data controller ship) if you have not done so previously. | Note: For GDPR questions of more general character or related to a specific GDPR-contract (e.g. data processing agreement or joint controllership agreements) the DTU GDPR-office offers support. | gdpr@dtu.dk | Personal Data Coordinator GDPR Office
|  | Mandatory | Create GDPR-cases in DTUDOCX and update GDPR related box in DTUDOCX Research case accordingly. |  | DTUDOCX | Personal data coordinator
| Consider manpower | Mandatory | Inform Department Management about the resources necessary on the project. |  |  | Project Office | Project Manager | Department Management approves employment
Collaborate on a plan for how to meet these needs.
|  |  | Check if special conditions regarding employment are mentioned in the Grant Letter or in guidelines (e.g. MSCA ITN PhD’s lønberegningskema Marie Curie). | Follow the HR recruitment and employment process for hiring new staff, incl. international employees regarding residence permit. In most cases, only the principal investigator (PI) can be hired fixed term without application. | Recruitment and onboarding | AHR
|  |  | Check PhD enrolment and tuition fee requirements, if applicable |  |  | AHR
|  |  | Check conditions for hourly paid staff, if applicable. |  |  | AHR
|  |  | Project Controller will assist in clarifying Funding Body’s annual hour standard. |  | Projekttype | Project Controller
|  |  |  | Consider time consumption associated with the hiring process. |  | AHR
As a rule, expect at least:
DK staff: 3-4 months plus resignation
EU staff: 4 months plus resignation
Non-EU: 6 months plus resignation
High-risk countries: more than 6 months (background check)
| Create a website |  |  | Create a project website, if required. |  | Project Office | Project Manager
3.2. Do ongoing project administration and budget follow-up
| Sub-task | Mandatory | Action | Considerations/Advice | Tool / Information | Who can help? | Who is responsible? | Who signs / approves?
| Check the project’s financial status |  | Check the financial status in DTU Fusion. | Make recurring transaction controlling: |  | Project Controller Project Office | Project Manager
|  |  |  | Are the actual costs correct? | Controlling af projectbudgetter og transaktioner
|  |  |  | Access the list of transactions under operational expenses in DTU Fusion. | DTU Fusion
Are the actual allocated hours correct? Consider hourly paid staff via e-forms.
Evaluate the remaining project period: Are the expected future costs correct?
Are the expected allocated hours correct?
| Consider changes in manpower |  |  | Ensure that changes in resource allocation are reflected in the project budget. | DTU Fusion | Project Controller Project Office | Project Manager
Tilpas løbende budgetter
| Consider Time sheets |  |  | If required by the Funding Body, fill out project-specific time sheets. These must comply with DTU Fusion and the Outlook calendar. |  | Project Office | Project Manager
Be aware of different requirements depending on the Funding Body.
| Is procurement compliant with rules? | Mandatory | Ensure that any procurement in the project is compliant with DTU’s procurement policy, incl. fixed assets. |  | Procurement | Procurement, Team Anlæg, AØR | Project Manager
|  | Filing mandatory | File documentation in the DTUDOCX Research case using the topic “Procurement documentation”. |  | DTUDOCX | DTUDOCX Support
| Time registration in DTU Fusion | Mandatory | All project participants must register all hours spent on the project. | Projekttimer => Faktuelle timer. AØR vejledning herom. | Timecard registration and allocation | The departments super user | Project Manager
| Consider travelling |  |  | If travelling is included in the project, then: |  | Project Office | Project Manager
Get a travel insurance card from the Department.
Book tickets and hotel via Carlson WagonLit.
Make a travel report in DTU Fusion.
Note: Important regarding travel for all projects: Project hours must be registered in DTU Fusion on the travelling days (align with the calendar) – otherwise the travel cost cannot be reimbursed.
| Correct the budget, if needed |  | Check whether the transactions on the project are correct. If not, consider re-allocation. Ask the Project Controller to correct transactions, if needed. | Be aware of local approval procedures. | Løbende drift | Project Controller | Project Manager
|  |  |  | Change resource allocation plans within or between projects. |  | Project Office
|  |  |  | Adjust task budgets. |  | Department Management Superuser for time allocation
|  | Filing mandatory |  | Adjust budgets, e.g. if additional funding is granted. Documentation must be filed in DOCX and sent in workflow to the Project Controller. | DTUDOCX | DOCX Support
3.3. Collaborate with partners
| Sub-task | Mandatory | Action | Considerations/Advice | Tool / Information | Who can help? | Who is responsible? | Who signs / approves?
| Plan meetings and conferences |  | Comply with any requirements in the Grant / Grant Letter / Investment Agreement about frequency and content of meetings. | When coordinating a project or being lead on a work package, the Project Manager most likely needs to plan and host meetings with partners and others. |  | Project Office | Project Manager
Take minutes of decisions (you may depend on them later).
| Host a virtual meeting |  |  | For virtual meetings use one of the DTU recommended platforms: Zoom or Microsoft Teams. |  | Project Office | Project Manager
| Host a face-to-face meeting or conference at DTU |  |  | DTU uses a.o. the conference system Conference Manager to organize, set-up and follow-up on conferences and congresses. | Read about conference planning and practical services at DTU Lyngby on Planning of scientific conferences - DTU Inside. | Project Office | Project Manager
|  |  |  | Get an overview of the meeting centres in 101 and 220 (Lyngby Campus) on DTU Inside. | Velkommen i Mødecenter 101 - DTU Inside
|  |  |  | Order catering (use links "Mødecenter…"). | Velkommen i Mødecenter 202 - DTU Inside
Create a guest login to DTU WIFI.
Use DTU conference materials with DTU logo. Consider DTU Merchandise.
| Decide on collaboration platforms |  | Choose a suitable platform to share files and collaborate virtually with other partners. |  |  |  | Project Manager
|  |  |  | Evaluate risks and document relevant information about processing and safety measures regarding data handling. Use apporpriate DTU solutions for collaboration and sharing data. |  | AIT
Note: You are not allowed to use platforms like Google Docs and Microsoft OneNote for research data storage due to transfer of ownership of data and uncertainty regarding data storage.
3.4. Make ongoing reporting
| Sub-task | Mandatory | Action | Considerations/Advice | Tool / Information | Who can help? | Who is responsible? | Who signs / approves?
| Prepare the scientific report |  | If coordinator/if no partners: |  |  |  | Project Manager
|  |  | Document the progress and outcome of the project. |  |  | Project Office
Monitor and comply with deadlines for the scientific reports.
Collect scientific reports / results from partners.
Consolidate scientific report.
Submit the scientific report to the Funding Body.
Share the report with the scientific partners (if applicable).
|  | Filing mandatory | File the report in DOCX. |  | DTUDOCX | DOCX Support
If partner:
|  | Filing mandatory | Send the DTU contribution of the scientific report to the Coordinator within the given timeframe of the contract, and file in DOCX. |  | DTUDOCX
| Collect financial reports from partners |  | If coordinator: |  |  |  | Project Manager
|  |  | Collect financial reports from partners, possibly in a template. |  | Koordinatorprojekter | Project Controller
| Prepare the financial report | Mandatory | Document that expenses match the scientific progress according to the budget. |  | Projektregnskab | Project Controller | Project Manager
|  |  | If coordinator/if no partners: | Make sure to keep track of deadlines for financial reports.
|  |  | Project Controller produces DTU financial report (incl. budget & transaction control) in collaboration with the Project Manager. | Make sure that all the partners send their financial reports in due time to meet the official deadline an coordinate with Project Controller so there is time to consolidate and get internal DTU approval. | Projektregnskab | Project Controller
|  |  | Project Controller produces consolidated financial report and gets Project Manager’s approval of the final consolidated financial report. | Consider extra time if the financial statements need approval from e.g. a steering committee. | Projektregnskab | Project Controller
|  |  | Project Controller sends the consolidated financial report to the Funding Body, cc. Project Manager and Project Office (Project Office must file it in DOCX when approval from the Funding Body is received). |  |  | DOCX Support
|  |  | Project Office sends template (Payment to Business Partners) to partners and forwards the response to Project Controller. |  |  | Project Office
|  |  | Project Controller produces invoice / payment request and send it to the Funding Body. |  | Anden controlling | Project Controller
If partner:
|  |  | Project Controller produces DTU financial report (incl. budget & transaction control) in collaboration with Project Manager. |  | Projektregnskab | Project Controller
|  |  | Project Controller sends the consolidated financial report to coordinator, cc. Project Manager and Project Office. |  | Projektregnskab | Project Controller
|  |  | Project Controller produces invoice / payment request and send it to the Funding Body / coordinator. |  | Projektdrift | Project Controller
| Prepare payment to partners |  | If coordinator: |  |  |  | Project Manager
|  |  | Send template (Payment to Business Partners) to partners and forward response to Project Controller. |  |  | Project Office
|  | Filing mandatory | File all written communication with external participants in DOCX. |  | DTUDOCX
| Prepare other reporting |  | Check whether the Grant Letter and guidelines require any additional reporting. | Note: Some Grant Authorities require additional reporting, e.g. on EU-MSCA-ITN project, where the enrolled PhDs must be registered on the “Funding & Tender Opportunities”, or special reporting on dissemination, ethics and/or gender aspects. |  | Project Office | Project Manager
Write and submit the report to the Funding Body.
|  | Filing mandatory | Upload the reports in DOCX. |  | DTUDOCX
3.5. If you make changes to the project
| Sub-task | Mandatory | Action | Considerations/Advice | Tool / Information | Who can help? | Who is responsible? | Who signs / approves?
| Making changes in the consortium (e.g. integrate a new partner) |  | In case of changes in the consortium or other adjustments in the project: | During the project lifetime, it may be necessary to update the contract and / or cooperation agreement. Changes may originate from partners, changes in the consortium or from progress related issues within the project. |  |  | Project Manager
|  |  | Discuss with Contract Responsible whether Legal must be involved. | In these cases, the consortium/collaboration agreement may call for adjustments or amendments. |  | Contract Responsible, Legal
Inform Project Office of name changes and contact details of partners.
| Inform about changes in partner details |  | Update DOCX with name changes and contact details of partners and send relevant information to Project Controller. |  | DTUDOCX |  | Project Office
| Making changes in the scientific plan |  | Write a request with arguments for changes in the project plan. | Identify any ethical issues that may arise as a result of the planned changes to your project, including the need for additional or amended ethical approvals, and explain how you will address them. If the changes do not give rise to ethical considerations beyond those already covered, ensure that this is clearly stated and justified. | Research ethics (ethical approvals, permits and other ethical concerns) | Project Office | Project Manager
Send the request to the Funding Body.
|  | Filing mandatory | File the request in DOCX. |  | DTUDOCX | DOCX Support
File the response from the Funding Body in DOCX.
| Making changes to the proccessing of personal data in the project | Filling mandatory | Update record of processing activities and file the revised record in DTUDOCX. Update or enter into new GDPR-agreement if e.g. project partners change, new processors are affiliated, new processing systems are applied etc.). New or revised agreements must be documented and filed in DTUDOCX. | Any changes to processing of personal data in the project must be documented and filed in DTUDOCX. | GDPR at DTU - Protection of personal data - DTU Inside | Personal Data Coordinator GDPR-office | Project Manager
| Re-budgetting |  | Identify the need for re-budgeting. | Most Funding Bodies have guidelines for re-budgeting, e.g. if expenses differ more than 10% from the budget, a re-budget is needed. |  | Project Controller | Project Manager
|  |  | Create a re-budget. |  | Projekttype | Project Office
Ask the Funding Body for approval of the new budget.
|  |  | Update DOCX with the above and await the Funding Body’s response. |  |  | DOCX Support
Upon reply, file the response in DOCX.
Send approval of the re-budget to the project partners.
|  | Filing mandatory | Send the approval to Project Controller via workflow in DOCX. |  | DTUDOCX
|  |  | Ensure changes are reflected in the internal budget. |  | Løbende projektopfølgning | Project Controller
| Asking for an extension |  | Write a request for an extension arguing for the background and consequences of an extension of the project, including changes in milestone and project plan. |  |  | Project Office | Project Manager
Send the request to the Funding Body.
|  | Filing mandatory | File the request in DOCX. |  | DTUDOCX
Wait for the Funding Body’s reply.
Inform the partners of the project extension.
|  |  | File the reply and send it to the Project Controller via DOCX. |  | DTUDOCX
3.6. Disseminate project results
| Sub-task | Mandatory | Action | Considerations/Advice | Tool / Information | Who can help? | Who is responsible? | Who signs / approves?
| Report scientific papers and data |  | Make sure that all all publicly available lists of papers, data and other output that result from the project, are updated, e.g. on the project website. | Remember to add Grant Agreement no. and project acronyms to publications - not only for EU grants. |  | DTU Library | Project Manager
|  | Mandatory | Register publication in DTU Orbit (orbit.dtu.dk). | Note: regarding EU projects: Publications in DTU Orbit as well as data, software and other outputs in DTU Data are harvested to Open AIRE and therefore available in the grant portal. | DTU Orbit
|  | Mandatory | Create an ORCID. |  | ORCID - your researcher ID
Research output - registration of research in DTU Orbit
| Identify and file intellectual property rights and patents/software | Mandatory | Ensure that intellectual property rights (IPR) are identified and filed according to DTU policy. |  | Patenter & Software - DTU Inside | Legal | Project Manager
|  |  | Follow DTU's software and patent procedures. |  | About Software - DTU Inside (login required) | Innovation Responsible at the Department
|  |  | Consider commercialization of inventions. |  | Submit a notification of invention (NOI)
|  |  | Fill in the relevant form for patents (notification of invention, NOI) and software (software notification form, SNF). |  | Software notification
| Consider PR and knowledge sharing on other media |  | Decide if and how to broadcast project results. | Consult the DTU policy and guidelines regarding communication and design. |  | The Department’s communication partner | Project Manager
Consider using non-scientific articles, press releases, news on DTU main site, Dynamo, Social Medias, talks etc.
Be prepared if journalists call.
| Publishing |  | Consider Open Access and FAIR/Open Data requirements when publishing. | Use a trusted data repository, such as DTU Data to publish data, code and related research outputs. | Open Access-publishing at DTU - DTU Library | DTU Library | Project Manager
|  |  |  | Consider whether informed consent, agreements, and legal requirements cover the intended publication or sharing of data/materials, including: whether participants have consented to how their data will be presented, shared, or published, including the level of anonymisation/identifiability; whether participants have agreed to be informed about research results; whether ABS permits or agreements include publication-related conditions (e.g. acknowledgement, reporting, or sharing publications with partners/providers of the genetic resource(s)). | DTU Data | DTU Library
|  |  | Ethics: Check that informed consent and agreement conditions are consistent with the intended publication or sharing of data/materials. |  | About DTU Data - DTU Library | DTU Library
| Maintain the project website |  | Decide if and how to maintain the project website during and after the project. |  |  | Project Office | Project Manager
3.7. Close the project
| Sub-task | Mandatory | Action | Considerations/Advice | Tool / Information | Who can help? | Who is responsible? | Who signs / approves?
| Close the project in the financial system |  |  |  | DTU Fusion | Project Controller | Project Manager
Projektlukning
| Close the project in DOCX |  | Close the research case in DOCX. | Note: Research cases in DOCX are automatically closed 1 year after project end date. | DTUDOCX | Project Office | Project manager
File Data Management Plan according to Department procedure.
| Close or ensure maintenance of project website |  | Decide on closure, extension or decommissioning of the website and domain. |  |  | Project Office | Project Manager
| Decide on long-term data storage |  | Check and comply with the requirements for long-term preservation of research data according to DMP. | Data repositories - National Archives - Local storage | Long term preservation of research data
[5 empty] | Guide to preservation in DTU data | DTU Library | Project Manager
| Delete, archive, anonymise or reuse personal data | Mandatory | Comply with relevant GDPR requirements on deletion, anonymisation or achiving of personal data from your project Close GDPR-case in DTUDOCX |  | DTUDOCX | Personal Data Coordinator | Project Manager